## Matrix
Policy Deployment Matrix
|  |  |  | X | Attend all regional golf events
|  |  |  | X | Visit 5 potential new clients | [9 empty] | X
|  |  |  | X | Re-design trade show booth and attend 5 trade shows | [6 empty] | X | X | X
|  |  | X |  | Hold safety meetings to ensure that all personnel are familiar with hazard assessment forms and know that they are mandatory. | [5 empty] | X
|  | X |  |  | Provide training for 7 project managers |  |  |  |  | X
| X |  |  |  | Investigate and purchase software for time tracking and invoicing. Convert previous data. Ensure seamless transition. |  | X | X | X
X |  |  |  |  | Prepare a standard report template that contains checklists for all report items and explanations as to what they should contain. | X
Improve report quality for preliminary engineering reports and assessments | Streamline time tracking, invoicing, and expense tracking | Provide training in Project Management to all PM's. | Ensure the company safety program is followed | Increase revenue by 20% |  | Develop Report Template by Nov. 30 | Purchase software by Apr. 30. | Provide software training by Jun. 30 | Implement on Jul. 31. Monitor effectiveness by talking to PM's on a bi-weekly basis. | Complete training by Aug. 31 | Hold safety meetings by Mar. 31. Monitor number of hazard assessments performed for 3 months. | Complete trade show booth by Mar. 31 | Attend AAMDC and tri-party shows | Attend 3 other trade shows by Dec. 31 | Visit potential clients by Jun. 30
Quality | Cost | People | Safety | Customers
X |  |  |  |  | Senior management to provide quality score
| X |  |  |  | Purchase software for time tracking & invoicing
|  | X |  |  | Provide training for 7 project managers
|  |  | X |  | Perform full hazard assessments for all field work
|  |  |  | X | Add at least 2 new clients within the year
|  |  |  | X | Ensure at least 3 touches to existing clients
PROJECTS
COMPANY
OBJECTIVES
COMPANY
TARGETS
IMPROVEMENT
TARGETS

## Implementation Plan
Objective: Prepare Standard Report Template
Task No. | Task | Metric | Owner | Target Date | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Identify previous reports to be used |  | B. Roseke | 2014-06-21 | Jan: 0%; Feb: 0%; Mar: 25%; Apr: 25%; May: 75%; Jun: 100%; Jul: 100%
2 | Develop primary report items |  | B. Roseke | 2014-07-20 | Jan: 0%; Feb: 0%; Mar: 0%; Apr: 0%; May: 25%; Jun: 100%; Jul: 100%
3 | Write typical sections |  | B. Roseke | 2014-08-15 | Jan: 0%; Feb: 0%; Mar: 0%; Apr: 0%; May: 0%; Jun: 0%; Jul: 25%
4 | prepare checklists under each report item |  | B. Roseke | 2014-08-31 | Jan: 0%; Feb: 0%; Mar: 0%; Apr: 0%; May: 0%; Jun: 0%; Jul: 25%
5 | Choose formatting |  | B. Roseke | 2014-09-30 | Jan: 0%; Feb: 0%; Mar: 0%; Apr: 0%; May: 0%; Jun: 0%; Jul: 25%
6 | Technical Review #1 |  | J. Smalley | 2014-10-31 | bar: Jan to Jul
7 | Technical Review #2 |  | L. Hammond | 2014-10-31 | bar: Jan to Jul
8 | Finalize |  | B. Roseke | 2014-11-30 | bar: Jan to Jul