## Build a House
Build a House
| ACTIVITY | START DATE | DURATION | END DATE | SEPTEMBER | [29 empty] | OCTOBER | [30 empty] | NOVEMBER | [29 empty] | DECEMBER
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Excavation
| Excavation | 2018-09-02 | 7 | 2018-09-12 | bar: SEPTEMBER 2 to SEPTEMBER 12
| Pour Concrete | 2018-09-13 | 4 | 2018-09-16 | bar: SEPTEMBER 13 to SEPTEMBER 16
| Backfill | 2018-09-19 | 3 | 2018-09-21 | bar: SEPTEMBER 19 to SEPTEMBER 21
| Framing | 2018-09-20 | 14 | 2018-10-07 | bar: SEPTEMBER 20 to OCTOBER 7
Mechanical/Electrical
| HVAC | 2018-10-10 | 10 | 2018-10-21 | bar: OCTOBER 10 to OCTOBER 21
| Plumbing | 2018-10-13 | 10 | 2018-10-26 | bar: OCTOBER 13 to OCTOBER 26
| Electrical | 2018-10-18 | 9 | 2018-10-28 | bar: OCTOBER 18 to OCTOBER 28
Finishing
| Drywall | 2018-09-28 | 2 | 2018-09-28 | bar: OCTOBER 31 to NOVEMBER 9
| Painting | 2018-11-10 | 9 | 2018-11-22 | bar: NOVEMBER 10 to NOVEMBER 22
| Flooring | 2018-11-23 | 9 | 2018-12-05 | bar: NOVEMBER 23 to DECEMBER 5
| Landscaping | 2018-11-21 | 23 | 2018-12-21 | bar: NOVEMBER 21 to DECEMBER 21

## Deliver a Shipment
Deliver a Shipment
| ACTIVITY | START DATE | DURATION | END DATE | SEPTEMBER | [29 empty] | OCTOBER | [30 empty] | NOVEMBER
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Planning
| Procure Delivery Firm | 2018-09-03 | 13 | 2018-09-19 | bar: SEPTEMBER 3 to SEPTEMBER 19
| Order Packaging Material | 2018-09-17 | 5 | 2018-09-21 | bar: SEPTEMBER 17 to SEPTEMBER 21
| Measure Size of Product | 2018-09-20 | 7 | 2018-09-28 | bar: SEPTEMBER 20 to SEPTEMBER 28
Loading
| Packaging | 2018-09-28 | 4 | 2018-10-03 | bar: SEPTEMBER 28 to OCTOBER 3
| Loading | 2018-10-03 | 2 | 2018-10-04 | bar: OCTOBER 3 to OCTOBER 4
| Hauling | 2018-10-05 | 10 | 2018-10-14 | bar: OCTOBER 5 to OCTOBER 14
Unloading
| Unloading | 2018-10-15 | 2 | 2018-10-16 | bar: OCTOBER 15 to OCTOBER 16
| Storage | 2018-10-15 | 29 | 2018-11-12 | bar: OCTOBER 15 to NOVEMBER 12
| Unpackaging | 2018-11-13 | 4 | 2018-11-16 | bar: NOVEMBER 13 to NOVEMBER 16
| Vehicle Return | 2018-10-15 | 8 | 2018-10-22 | bar: OCTOBER 15 to OCTOBER 22

## Write a Report
Write a Report
| ACTIVITY | START DATE | DURATION | END DATE | MARCH | [30 empty] | APRIL | [29 empty] | MAY | [30 empty] | JUNE
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Preliminary
| Meet with Client | 2019-03-04 | 3 | 2019-03-06 | bar: MARCH 4 to MARCH 6
| Visit Site | 2019-03-07 | 7 | 2019-03-15 | bar: MARCH 7 to MARCH 15
| Gather Data | 2019-03-11 | 8 | 2019-03-20 | bar: MARCH 11 to MARCH 20
| Interview Stakeholders | 2019-03-13 | 8 | 2019-03-22 | bar: MARCH 13 to MARCH 22
Analysis
| Analyze Data | 2019-03-21 | 22 | 2019-04-19 | bar: MARCH 21 to APRIL 19
| Develop Alternatives | 2019-04-01 | 25 | 2019-05-03 | bar: APRIL 1 to MAY 3
| Prepare Cost Estimates | 2019-04-22 | 18 | 2019-05-15 | bar: APRIL 22 to MAY 15
| Hold Consultations | 2019-04-22 | 25 | 2019-05-24 | bar: APRIL 22 to MAY 24
Write Report
| Write Report | 2019-05-01 | 23 | 2019-05-31 | bar: MAY 1 to MAY 31
| Submit Draft to Client | 2019-05-31 | 1 | 2019-05-31 | bar: MAY 31
| Review Meetings and Revisions | 2019-06-03 | 19 | 2019-06-27 | bar: JUNE 3 to JUNE 27
| Submit Final Report | 2019-06-28 | 1 | 2019-06-28 | bar: JUNE 28

## Science Fair Project
Science Fair Project
| TASK | START DATE | DURATION | END DATE | JANUARY | [30 empty] | FEBRUARY | [27 empty] | MARCH | [30 empty] | APRIL
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Submit Project Description | 2019-01-08 | 1 | 2019-01-08 | bar: JANUARY 8
Planning
| Create Plans | 2019-01-09 | 13 | 2019-01-25 | bar: JANUARY 9 to JANUARY 25
| Determine Supplies | 2019-01-14 | 10 | 2019-01-25 | bar: JANUARY 14 to JANUARY 25
| Purchase Supplies | 2019-01-28 | 5 | 2019-02-01 | bar: JANUARY 28 to FEBRUARY 1
Construct Project
| Build Section 1 | 2019-02-04 | 15 | 2019-02-22 | bar: FEBRUARY 4 to FEBRUARY 22
| Build Section 2 | 2019-02-18 | 10 | 2019-03-01 | bar: FEBRUARY 18 to MARCH 1
| Build Section 3 | 2019-02-25 | 15 | 2019-03-15 | bar: FEBRUARY 25 to MARCH 15
| Assemble Prototype | 2019-03-12 | 14 | 2019-03-29 | bar: MARCH 12 to MARCH 29
Refine and Finish
| Refine Prototype | 2019-04-01 | 11 | 2019-04-15 | bar: APRIL 1 to APRIL 15
| Write Report / Document | 2019-04-01 | 12 | 2019-04-16 | bar: APRIL 1 to APRIL 16
| Science Fair | 2019-04-17 | 1 | 2019-04-17 | bar: APRIL 17

## Parking Lot Paving
Parking Lot Paving
| ACTIVITY | START DATE | DURATION | END DATE | JUNE | [29 empty] | JULY | [30 empty] | AUGUST
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Preparation
| Perform Utility Locates | 2019-06-03 | 15 | 2019-06-21 | bar: JUNE 3 to JUNE 21
| Place Barricades | 2019-07-24 | 2 | 2019-07-25 | bar: JUNE 24 to JUNE 25
| Milling & Filling | 2019-07-25 | 7 | 2019-08-03 | bar: JUNE 25 to JULY 3
| Place Base Gravel | 2019-06-28 | 16 | 2019-07-19 | bar: JUNE 28 to JULY 19
| Pour Concrete Curbs | 2019-07-10 | 13 | 2019-07-26 | bar: JULY 10 to JULY 26
Paving
| Tack Coat | 2019-07-29 | 1 | 2019-07-29 | bar: JULY 29
| Asphalt Paving | 2019-07-29 | 2 | 2019-07-30 | bar: JULY 29 to JULY 30
| Materials Testing | 2019-07-30 | 2 | 2019-07-31 | bar: JULY 30 to JULY 31
Finishing
| Paint Lines | 2019-08-05 | 15 | 2019-08-16 | bar: AUGUST 5 to AUGUST 16
| Remove Concrete Forms | 2019-08-01 | 7 | 2019-08-09 | bar: AUGUST 1 to AUGUST 9
| Landscaping | 2019-08-07 | 14 | 2019-08-26 | bar: AUGUST 7 to AUGUST 26
| Remove Barricades | 2019-08-27 | 1 | 2019-08-27 | bar: AUGUST 27

## Habitat Restoration Project
Habitat Restoration Project
| ACTIVITY | START DATE | DURATION | END DATE | JULY | [30 empty] | AUGUST | [30 empty] | SEPTEMBER | [29 empty] | OCTOBER
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Baselining
| Set up Monitoring Devices | 2019-07-08 | 2 | 2019-07-09 | bar: JULY 8 to JULY 9
| Monitoring | 2019-07-10 | 23 | 2019-08-09 | bar: JULY 10 to AUGUST 9
| Data Analysis | 2019-07-29 | 20 | 2019-08-23 | bar: JULY 29 to AUGUST 23
| Report | 2019-08-12 | 15 | 2019-08-30 | bar: AUGUST 12 to AUGUST 30
Design
| Plans & Profiles | 2019-09-02 | 9 | 2019-09-12 | bar: SEPTEMBER 2 to SEPTEMBER 12
| Design Report | 2019-09-05 | 12 | 2019-09-20 | bar: SEPTEMBER 5 to SEPTEMBER 20
| Review Meetings & Revisions | 2019-09-23 | 10 | 2019-10-04 | bar: SEPTEMBER 23 to OCTOBER 4
Construction
| Mobilization | 2019-10-10 | 2 | 2019-09-11 | bar: OCTOBER 10 to OCTOBER 11
| Construction | 2019-10-14 | 7 | 2019-10-22 | bar: OCTOBER 14 to OCTOBER 22
| Testing | 2019-10-21 | 2 | 2019-10-22 | bar: OCTOBER 21 to OCTOBER 22
| Install Long Term Monitoring | 2019-10-22 | 3 | 2019-10-24 | bar: OCTOBER 22 to OCTOBER 24

## Plan an Event
Plan an Event
| ACTIVITY | START DATE | DURATION | END DATE | NOVEMBER 2019 | [29 empty] | DECEMBER 2019 | [30 empty] | JANUARY 2020 | [30 empty] | FEBRUARY 2020
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Invitations
| Finalize Attendee List | 2019-11-04 | 7 | 2019-11-11 | bar: NOVEMBER 2019 4 to NOVEMBER 2019 11
| Create Invitations | 2019-11-11 | 5 | 2019-11-15 | bar: NOVEMBER 2019 11 to NOVEMBER 2019 15
| Send Invitations | 2019-11-18 | 2 | 2019-11-19 | bar: NOVEMBER 2019 18 to NOVEMBER 2019 19
Preparations
| Book Meeting Space | 2019-11-20 | 8 | 2019-11-29 | bar: NOVEMBER 2019 20 to NOVEMBER 2019 29
| Determine Equipment | 2019-12-02 | 8 | 2019-12-11 | bar: DECEMBER 2019 2 to DECEMBER 2019 11
| Order/Procure Equipment | 2019-12-09 | 25 | 2020-01-10 | bar: DECEMBER 2019 9 to JANUARY 2020 10
| Prepare Presentation(s) | 2019-12-05 | 32 | 2020-01-17 | bar: DECEMBER 2019 5 to JANUARY 2020 17
Event
| Prepare Venue | 2020-01-20 | 2 | 2020-01-21 | bar: JANUARY 2020 20 to JANUARY 2020 21
| Hold Event | 2020-01-22 | 3 | 2020-01-24 | bar: JANUARY 2020 22 to JANUARY 2020 24
Post-Event
| Prepare Slide Show | 2020-01-27 | 15 | 2020-02-14 | bar: JANUARY 2020 27 to FEBRUARY 2020 14
| Send Follow-up Email | 2020-02-27 | 5 | 2020-02-21 | bar: FEBRUARY 2020 17 to FEBRUARY 2020 21

## Build a New Shop
Build a New Shop
| ACTIVITY | START DATE | DURATION | END DATE | SEPTEMBER | [29 empty] | OCTOBER | [30 empty] | NOVEMBER | [29 empty] | DECEMBER
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Excavation
| Excavation | 2018-09-02 | 7 | 2018-09-12 | bar: SEPTEMBER 2 to SEPTEMBER 12
| Pour Concrete | 2018-09-13 | 4 | 2018-09-16 | bar: SEPTEMBER 13 to SEPTEMBER 16
| Backfill | 2018-09-19 | 3 | 2018-09-21 | bar: SEPTEMBER 19 to SEPTEMBER 21
| Framing | 2018-09-20 | 14 | 2018-10-07 | bar: SEPTEMBER 20 to OCTOBER 7
Mechanical/Electrical
| HVAC | 2018-10-10 | 10 | 2018-10-21 | bar: OCTOBER 10 to OCTOBER 21
| Plumbing | 2018-10-13 | 10 | 2018-10-26 | bar: OCTOBER 13 to OCTOBER 26
| Electrical | 2018-10-18 | 9 | 2018-10-28 | bar: OCTOBER 18 to OCTOBER 28
Finishing
| Drywall | 2018-09-28 | 2 | 2018-09-28 | bar: OCTOBER 31 to NOVEMBER 9
| Painting | 2018-11-10 | 9 | 2018-11-22 | bar: NOVEMBER 10 to NOVEMBER 22
| Flooring | 2018-11-23 | 9 | 2018-12-05 | bar: NOVEMBER 23 to DECEMBER 5
| Landscaping | 2018-11-21 | 23 | 2018-12-21 | bar: NOVEMBER 21 to DECEMBER 21

## Develop a Manual
Develop a Manual
| ACTIVITY | START DATE | DURATION | END DATE | MARCH 2019 | [30 empty] | APRIL 2019 | [29 empty] | MAY 2019 | [30 empty] | JUNE 2019
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Preparation
| Learn Device | 2019-03-04 | 17 | 2019-03-26 | bar: MARCH 2019 4 to MARCH 2019 26
| Learn Functions | 2019-03-18 | 10 | 2019-03-29 | bar: MARCH 2019 18 to MARCH 2019 29
| Interview Users | 2019-03-25 | 8 | 2019-04-03 | bar: MARCH 2019 25 to APRIL 2019 3
| Interview Management | 2019-03-28 | 10 | 2019-04-10 | bar: MARCH 2019 28 to APRIL 2019 10
Write Manual
| User Guide | 2019-04-08 | 20 | 2019-05-03 | bar: APRIL 2019 8 to MAY 2019 3
| Getting Started Guide | 2019-04-22 | 20 | 2019-05-03 | bar: APRIL 2019 22 to MAY 2019 17
| Finalize Documents | 2019-05-20 | 7 | 2019-05-28 | bar: MAY 2019 20 to MAY 2019 28
| Review Meetings and Revisions | 2019-05-30 | 9 | 2019-04-10 | bar: MAY 2019 29 to JUNE 2019 10
| Translation | 2019-06-11 | 10 | 2019-06-24 | bar: JUNE 2019 11 to JUNE 2019 24
| Printing | 2019-06-11 | 11 | 2019-06-25 | bar: JUNE 2019 11 to JUNE 2019 25
| Distribution | 2019-06-26 | 3 | 2019-06-28 | bar: JUNE 2019 26 to JUNE 2019 28
| Project Closing | 2019-06-28 | 1 | 2019-06-28 | bar: JUNE 2019 28

## Develop a New Product
Develop a New Product
| ACTIVITY | START DATE | DURATION | END DATE | AUGUST 2019 | [30 empty] | SEPTEMBER 2019 | [29 empty] | OCTOBER 2019 | [30 empty] | NOVEMBER 2019
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Research & Development
| Market Research | 2019-08-02 | 10 | 2019-08-15 | bar: AUGUST 2019 2 to AUGUST 2019 15
| Product Research | 2019-08-06 | 12 | 2019-08-21 | bar: AUGUST 2019 6 to AUGUST 2019 21
| Preliminary Design | 2019-08-19 | 12 | 2019-09-03 | bar: AUGUST 2019 19 to SEPTEMBER 2019 3
| Write Report | 2019-09-02 | 5 | 2019-09-06 | bar: SEPTEMBER 2019 2 to SEPTEMBER 2019 6
Design
| Detailed Design | 2019-09-09 | 17 | 2019-10-01 | bar: SEPTEMBER 2019 9 to OCTOBER 2019 1
| Determine Quantities | 2019-09-19 | 9 | 2019-10-01 | bar: SEPTEMBER 2019 19 to OCTOBER 2019 1
| Cost Estimates | 2019-09-25 | 5 | 2019-10-01 | bar: SEPTEMBER 2019 25 to OCTOBER 2019 1
Manufacturing
| Procure Suppliers | 2019-10-02 | 17 | 2019-10-24 | bar: OCTOBER 2019 2 to OCTOBER 2019 24
| Purchase Materials | 2019-10-15 | 16 | 2019-11-05 | bar: OCTOBER 2019 15 to NOVEMBER 2019 5
| Build Production Facilities | 2019-10-02 | 40 | 2019-11-26 | bar: OCTOBER 2019 2 to NOVEMBER 2019 26
| Produce First Product | 2019-11-27 | 1 | 2019-11-27 | bar: NOVEMBER 2019 27